## Sheet1
# |  | Task Force Recommendations | Tasks | Start Date | End Date | Owner | Status/Comments
1 | Need Identification | Identify student behavioral health needs for all District public and public charter schools. |  | March 27, 2018 | May 1, 2018
|  | Use available population and student level data, including the OSSE At-Risk formula, students with an Individual Education Plan, student absenteeism, students receiving out-of-school suspension, and other data as determined appropriate. | Decide on data elements for Year 1 Need Identification.
|  | Consider the proper weight to give each element. | Analyze data using different weights for the OSSE At-Risk Formula.
|  | Look at whether and how the differences in the data for Elementary, Middle, and High Schools should be taken into account. | Analyze and compare the data using an "all schools" dataset and using a dataset where schools are grouped by type.
Bring completed data analyses to Coordinating Council's April meeting for final guidance/input.
Share need identification results with schools and other stakeholders, including an FAQ
Define process for refining need identification for year #2
2 | Year 1 Implementation | Begin implementation of the model in SY 2018-2019 in the 53 schools that are the top 25% of schools by behavioral health indicators.
Determine "unmet need" for each Yr. 1 school through at least two inputs (1) identifying resources currently in school and comparing to fleshed out District SMH Model Standard; and (2) school readiness/needs assessment.
Develop "on-boarding"process for schools, including communications, timetables, staff resources, and roles and responsibilities between DBH and Education partners.
Develop school-wide plan format and elements that schools will use to document their school's needs, resources, strategies, timeline, and roles & responsibilities.
Develop and launch a robust school awareness campaign to make all DCPS and Public Charter schools aware of all available behavioral health resources across all tiers, including crisis services, and continue to support the continued growth in Tier 1, 2, and 3 services in all schools.
|  | Provide $1,901,000 in grant funding to community-based behavioral health providers to support 33 clinicians and 4 clinical supervisors. Grant funds will support CBOs to provide, in addition to billable clinical services, non-billable interventions and supports integral to a multi-tiered school-based practice, including but not limited to teacher and parent consultation, school team meetings, care coordination, and crisis management. | Complete grant process for the $1,901,000 in grant funding to community-based behavioral health providers to support about 33 clinicians and 4 clinical supervisors. Grant funds will support CBOs to provide, in addition to billable clinical services, non-billable interventions and supports integral to a multi-tiered school-based practice, including but not limited to teacher and parent consultation, school team meetings, care coordination, and crisis management; | May 1, 2018 See DBH Grant Process & Timeline for School-Based Behavioral Health Expansion Grants | October 15, 2018
|  | Provide $524,000 to develop a robust and effective Community of Practice to increase provider and school readiness and ability to implement the multi-tiered model. These funds can also support technical assistance to providers, schools, and to fund coordination support. | Complete procurement process for organization to develop and launch a Community of Practice and provide technical assistance to increase provider and school readiness and ability to implement the multi-tiered model. | May 1, 2018 See DBH Grant Process & Timeline for School-Based Behavioral Health Expansion Grants | October 15, 2018
|  | Provide $450,000 to fund 5 DBH contracted clinicians to provide interim support in Year #1 while CBOs build their capacity | Complete HR tasks to hire 5 DBH clinicians on a term basis to provide interim/flexible support and clinical resources in Year #1 while CBOs build their capacity.
Define scope of work for school crisis response assessment and complete agreement with the Lab @ DC to conduct assessment.
Invest $125,000 to support an evaluation of the first year of implementation, including an assessment of school-based crisis intervention services and response.
3 | Evaluation & Data | Provide $125,000 to support an evaluation of the first year of implementation, including an assessment of school-based crisis intervention services and response.
Develop Measures of Success
Develop evaluation plan, including how to measure school, parent & provider satisfaction?
Determine the data needed to measure success and areas needing improvement?
Determine data sharing requirements and agreements if needed.
| Role of the DBH School Mental Health Clinicians | In Year 1, keep the role of the DBH SMHP Clinician as currently defined, with the flexibility to provide Tier 1, Tier 2, and/or Tier 3 supports in their assigned schools.
Generally the Task Force does not recommend a change in resources among schools as a result of focusing on the highest need schools, however, Year #1 may necessitate reassignment of some DBH SMHP clinicians to different schools. If this occurs, DBH will work with the school and other partners to develop a transition plan to support continuity of care for students.
Discussion of future changes to the role of the DBH SMHP Clinician should include DBH clinicians and their representatives and be guided by input from the Coordinating Council and Governance entity and informed by an evaluation of resources available to replace those Tier 2 and Tier 3 services that would no longer be provided by the DBH clinician, with the goal of avoiding an unintended reduction in clinical services in schools served by DBH clinicians.
6 | Governance | Create an effective governance body and/or structure that holds agencies and participating stakeholders accountable for timely implementation of the expanded School-based Behavioral Health System.
|  |  | Invite BWG, Task Force, and other stakeholders to participate in the Coordinating Council and convene no later than April 20, 2018. | March 27, 2018 | April 20, 2018
Develop Coordinating Council governing documents.
All CC members complete ethics training