## Sheet1
# | Title | Main Recommendation | Additional Details of Recommendation | Tasks | Interim Milestones | Major Milestones | Time Table | Owner
1 | Need Identification | Identify student behavioral health needs for all District public and public charter schools. |  | Define all District public and public charter schools for purposes of Phase I (e.g., all DCPS & DCPCS except charter schools withonly pre-K, adult education schools, schools in secure facilities (at New Beginnings) | Complete data analyses per recommendations and synthesize results. | Need Identification completed.
|  |  | Use available population and student level data, including the OSSE At-Risk formula, students with an Individual Education Plan, student absenteeism, students receiving out-of-school suspension, and other data as determined appropriate. | No changes at this time | Bring completed data analyses to Coordinating Council's April meeting for final guidance/input. | Identify top 25% of schools by behavioral health needs
|  |  | Consider the proper weight to give each element. | DBH ran data with 2x weight. | Draft process for updating as needed (e.g., to correct errors or account for new information) | Finalize process for updating as needed (e.g., to correct errors or account for new information)
|  |  | Look at whether and how the differences in the data for Elementary, Middle, and High Schools should be taken into account. | DBH will run the data by each type of school and see how that differs from when data is run for all schools together.
Share need identification results with schools and other stakeholders, including an FAQ
Define process for refining need identification for year #2
2 | Phased Implementation and Year 1 | Prioritize implementation in Year #1 (SY 2018-19) in the top 25% of schools identified by behavioral health need from highest to lowest.
|  |  | For each school prioritized for Year #1 implementation, the District will build upon existing resources in these schools to develop a school-wide plan for assessment, primary prevention, and provision of Tier 2 and Tier 3 services through school and community-based partners, tailored to the needs of that school, and including provision of support to increase school readiness as needed. | Decide on school-wide plan format and elements, school readiness assessment tool and infrastructure to support completion of these plans, including roles and responsibilities among school and DBH partners. | Communications Plan to all schools, both priority schools for Year 1, and all other schools explaining the new | Roll out school-wide plan with directions and explanation of support structure, timeline, resources, etc.
|  |  | Assess the type and amount of crisis response resources available and whether those resources are sufficient to meet the need, especially given the expansion of access to Tiers 1 through Tier 3 in the year #1 implementation. | Define scope of work for school crisis response assessment and agreement with the Lab @ DC to conduct assessment.
|  |  | Ensure all DCPS and Public Charter schools are aware of all available behavioral health resources across all tiers, including crisis services, and continue to support the continued growth in Tier 1, 2, and 3 services in all schools. | Develop a robust school awareness campaign to make all DCPS and Public Charter schools aware of all available behavioral health resources across all tiers, including crisis services, and continue to support the continued growth in Tier 1, 2, and 3 services in all schools. | Draft school awareness campaign.
Create Implementation Work Plan for year #1.
3 | Role of the DBH School Mental Health Clinicians | In Year 1, keep the role of the DBH SMHP Clinician as currently defined, with the flexibility to provide Tier 1, Tier 2, and/or Tier 3 supports in their assigned schools. | Generally the Task Force does not recommend a change in resources among schools as a result of focusing on the highest need schools, however, Year #1 may necessitate reassignment of some DBH SMHP clinicians to different schools. If this occurs, DBH will work with the school and other partners to develop a transition plan to support continuity of care for students.
Discussion of future changes to the role of the DBH SMHP Clinician should include DBH clinicians and their representatives and be guided by input from the Coordinating Council and Governance entity. In addition, a discussion of change should be informed by an evaluation of resources available to replace those Tier 2 and Tier 3 services that would no longer be provided by the DBH clinician, with the goal of avoiding an unintended reduction in clinical services in schools served by DBH clinicians.
4 | Support Providers and Schools to Expand | To support successful expansion of school-based behavioral health the District should develop a Community of Practice and provide technical assistance to help providers and schools increase their readiness and capacity to implement the new model. | Develop a Community of Practice to share best practices, develop training, and improve communications among schools, public and private provider agencies, and family stakeholders. | Research existing DC Communities of Practice to understand how they were started and how they operate.
|  |  | Provide mentoring and technical assistance for providers. | Develop RFP for organization to develop and conduct a Community of Practice and provide technical assistance to providers and schools.
Provide mentoring and technical assistance for schools.
5 | Budget Recommendations | Provide $3,000,000 in additional funding in the FY 2019 budget for year 1 implementation through increased partnerships with community-based organizations and a short-term expansion of the DBH School Mental Health Program. | Invest $1,901,000 in grant funding to community-based behavioral health providers to support 33 clinicians and 4 clinical supervisors. Grant funds will support CBOs to provide, in addition to billable clinical services, non-billable interventions and supports integral to a multi-tiered school-based practice, including but not limited to teacher and parent consultation, school team meetings, care coordination, and crisis management; | Develop RFP to award grants to community-based behavioral health providers.
|  |  | Invest $450,000 to fund 5 DBH contracted clinicians to provide interim support in Year #1 while CBOs build their capacity. | Complete HR tasks to hire 5 clinicians on a contract basis.
|  |  | Invest $524,000 to develop a robust and effective Community of Practice to increase provider and school readiness and ability to implement the multi-tiered model. These funds can also support technical assistance to providers, schools, and to fund coordination support. | Develop RFP for organization to develop and conduct a Community of Practice and provide technical assistance to providers and schools. (Same)
|  |  | Invest $125,000 to support an evaluation of the first year of implementation, including an assessment of school-based crisis intervention services and response. | Develop evaluation plan and related agreements.
6 | Governance | Create an effective governance body and/or structure that holds agencies and participating stakeholders accountable for timely implementation of the expanded School-based Behavioral Health System. |  | Invite BWG, Task Force, and other stakeholders to participate in the Coordinating Council.
Develop Coordinating Council governing documents.